## Slide 1
NATIONAL SUPPLY CHAIN ASSESSMENT (NSCA2.0) STAKEHOLDER TRAINING
Day 2: Data Collection Overview
--:--am/pm : --:--am/pm
--/--/----
USAID Global Health Supply Chain Program - Technical Assistance - National Supply Chain Assessment Task Order

## Slide 2: Objective/Outline
  Objective: To have a summary view of how all the data collection work operates during the collection period.
  Graphic- of overall operations.
  Daily schedule.
Notes: This slide lays out the outline of this session giving an overall picture and timelines for the process. Subsequent sessions will go into further detail.

## Slide 3
Data Collection Operations
Notes: This slide shows 10 steps for the data collection operations:
1.) Deploying data collection teams: data collection should be ongoing at the central level and peripheral levels simultaneously.
2.) For the team composition you will want to minimize data collector bias – make sure you aren’t sending them to areas they know already. Make sure you aren’t leading the question and telling the respondent how to answer.
3.) In addition to the positions listed on the slide the core assessment team should also include a logistics coordinator to resolve problems and if the teams need to be rerouted.
4.) The timeline is determined by the number of sites to visit and the number of teams available. The available time for the assessment and the number of sites to visit will dictate the number of teams needed. The number of sites and time available (and therefore the number of teams) should be discussed and planned at the outset.
5.) Communication is key. We have successfully used WhatsApp for the Central team to be able to communicate efficiently with the field teams and for the field teams to communicate with one another.
6.) Authorization documents: Obtain a letter from the MOH authorizing the activity and share with the health facilities ahead of time. Bring copies with you. Plan to conduct courtesy calls at the relevant provincial and/or district health office before going to the facilities.
7.) Tasks: 1 or more people to do CMM and 1 or more to do KPIs. Can switch between facilities if desired.
8.) Need to have at least two tablets per team, one for CMM and one for KPI collection.
9.) Teams should upload the completed form at the end of each day. The data manager at central level needs to do quality checks at the end of each day and contact the field teams with questions.
10.) As mentioned before, teams should not be go to facilities they work in or supervise to avoid bias. Teams need to record the information as relayed by the facilities and not what the data collectors know the answer is. It is an important finding if facilities are not aware of certain procedures or responses (e.g. min/max stock levels).

## Slide 4: Daily Schedule I
Date | Activity
Day 0 | Data Collection Training Ends.
Day 1 | Set up a control tower and means of communication (WhatsApp) to communicate and handle issues encountered by data collection team.
Day 2 | Finalize logistics and data collection plans
Day 3 | Deployment of data collection teams
Day 4 | Data collection for sites 1 to 10
Day 5 | Data collection for sites 11 to 20 + Central Level
Day 6 | Data collection for sites 21 to 30 + Central Level
Day 7 | Data collection for sites 31 to 40 + Central Level
Day 8 | Data collection for sites 41 to 50 + Central Level
Day 9 | Data collection team returns to the capital city
Notes: This schedule is based on 10 data collection teams. Based on the distance needed to reach the sites, some teams may need to leave earlier than the day before data collection. If training ends on a Friday. Teams will depart on Saturday or Sunday. If it is a large country teams will not return to the capital city over the weekend.

## Slide 5: Daily Schedule II
Date | Activity
Day 10-11 | Assessment Coordinator organizes team meeting to discuss data collection, preliminary findings, lessons learned, action items and plan for week 2. Deploy teams for week two data collection (depending on size of the country teams may be not need a second deployment).
Day 12 | Data collection for sites 51 to 60
Day 12 | Assessment Coordinator team meeting to discuss and agree on materials and content for the Donor and MOH debrief
Day 13 | Data collection for sites 61 to 75 + Debrief with Donor @ Central Level
 | Assessment Coordinator (International consultant) to meet with Donor and TA partner to discuss and agree on materials and content for the MOH debrief
Day 14 | Debrief with MOH. Debrief with data collectors.
Day 15 | Departure
Notes: Departure refers to the end of the data collection exercise. If international consultants are involved this will be departure from country, otherwise it is meant to mark the conclusion of the field work. It is helpful to debrief with the data collectors as a group to discuss the preliminary findings so the data collectors can see how the information will be used. It also serves as an opportunity to gather overall impressions and get feedback on the tool.