## Slide 1
NATIONAL SUPPLY CHAIN ASSESSMENT (NSCA2.0) STAKEHOLDER TRAINING
Day 2: Managing Operations
--:--am/pm : --:--am/pm
--/--/----
USAID Global Health Supply Chain Program - Technical Assistance - National Supply Chain Assessment Task Order

## Slide 2: Objective/Outline
  Objective: Call out actions and tools to keep data collection running smoothly.
  Tracking progress.
  Maintaining consistency/Data QC.
  Common Issues and Resolution

## Slide 3: Tracking Progress
• During data collection, the team at center monitors and tracks data collection progress by:
  Confirming sampled sites visited.
  Confirming data is collected on-time and in the right locations.
  Resolving any issue arise that could adversely impact data collection, e.g., compare completed data forms with geolocation markers that have been uploaded into SurveyCTO with the data collection schedules to validate if data collection teams were physically present in the appropriate locations at the appropriate times.
Notes: TOR with clearly defined necessary qualifications and roles/responsibilities, tasks to be performed, and deliverables for assessment personnel. The central team needs to be able to respond to questions from the field teams. They may need to select alternate facilities (from the extra facilities drawn in the sample) if some facilities are closed or deemed not appropriate or make adjustments to the schedule. The central level teams needs to ensure the forms being uploaded are for the correct facility and confirm the level of the health facility was correct in the sample (e.g. hospital or health center).

## Slide 4: Maintaining Consistency/Data quality assurance
Form WhatsApp or similar group
Field questions in real time
Problem solve in real time
All teams see questions answers
Progress updates
Develop team unity among data collectors
Central team
Monitor schedule
Review data daily
Check geolocation
Check skip patterns
Check common errors on KPIs
Review ‘text’ answers and clarify with data collection teams
Notes: If the central team revises one of the data collection forms it can be uploaded to SurveyCTO. The central team notifies the field teams of the new form via WhatsApp so they can download it before going to the next facility.

## Slide 5: Things to monitor
“Other, specify”
Multiple selections (“none of the above, I don’t know”)
Notes at the end of each module
Commodity not managed
‘Adjusted amount’
‘Vacancies’
Notes: If the data collector selects other, they should type something in. During the data cleaning the data manager then decides if this is truly a separate response, or actually fits within one of the options. The notes at the end of the module can alert the data manager to a problem with the data collection, or other important findings.

## Slide 6: Common Issues and Resolution 1
Potential Data Collection Challenge | Possible Solutions
Deviation from data collection schedule | It takes time to schedule and assess sites in the midst of many competing activities. Use flexible data collection plans and schedules with contingencies to modify field travel plans as needed within set parameters. Design and use appropriate tools to track progress and compliance of data collection teams with set schedules and manage or correct deviations before it’s too late. Make sure approved changes to the data collection schedule are properly documented.
Notes: Bullet 2: (e.g. as long as they maintain the assigned sample of sites and communicate accordingly for Central Coordination Unit approval). When the sample of sites is selected there should be some extra sites selected in case replacements are needed. The central team will let the field team know where to go and how to record this (the new facility name may not have been included in the options in SurveyCTO).

## Slide 7: Common Issues and Resolution 1I
Potential Data Collection Challenge | Possible Solutions
Difficulty accessing data | If it’s LMIS/eLMIS data that is not accessible, find out from the health facility who is responsible and has access or can help you access the data. To avoid running into such access problems, alert the sites in advance on what data to be collected, and release of data is approved. Request for the data to be submitted electronically or by downloading eLMIS data before the site visit. Make sure data collectors hold introductory/in-briefing sessions with host site staff and request the right, knowledgeable HF staff to assist them.
Notes: If you are interviewing someone new to the facility you may want to ask if you can speak with someone who has been at the facility for a longer period of time who can provide more insight into the operations at this facility. The best thing is to alert the facility in advance of what you will need for verification. If this is at the central level you may need to make return trips to collect this information. Do not rely on the staff to email you the information. Have a back up plan to return to the central level facility if needed to collect the data.

## Slide 8: Common Issues and Resolution 1II
Potential Data Collection Challenge | Possible Solutions
Transportation challenges | Plan field logistics (including securing safe and well serviced vehicles). Provide data collection teams with appropriate vehicles for the terrain and/or weather conditions, and provide adequate gasoline storage capacity and/or reserve gasoline, frequently needed spare parts for teams traveling to remote areas. Schedule to travel during appropriate times to avoid interruptions or unsafe travel, consider public holidays, and planned or possible competing activities at the sites to be visited. Provide data collection teams with optimized routings. Proactively investigate and understand the nature and contributory factors for the transportation problems.

## Slide 9: Common Issues and Resolution 1V
Potential Data Collection Challenge | Possible Solutions
Data collectors face problems using tablet PCs, CMM/KPI data collection instruments, or any other issues that may arise during capability interviews or KPI data collection | Set up and use WhatsApp group or other appropriate social media platform to enable real time, two-way coordination and communication between the central coordination unit and field teams, and communication among field teams to share experiences and advise each other on solving data collection problems in real time The Data Manager should remotely support the field teams from the central unit by providing real-time answers to any enquiries, and help promptly solve field challenges. Central unit to upload modified forms if needed Field teams should have paper forms as backup

## Slide 10: Common Issues and Resolution V
Potential Data Collection Challenge | Possible Solutions
Data quality issues/missing data | Data Manager should continuously check uploaded data for errors, inconsistencies, missing data or other quality issues, and proactively reach out and follow up to address the problems. Properly document any changes made based on the data cleaning and quality assurance process.
Notes: The quality of assessment data and results can be impacted by errors introduced into the data during data collection. There measures that one could put in place to mitigate the risk of error.

## Slide 11: Common Issues and Resolution VI
Potential Data Collection Challenge | Possible Solutions
Inadequate knowledge of health system among data collection team | Utilize data collectors who are existing players in the country supply chain and are knowledgeable of the health system, as long as data collectors are assigned to assess outside of their own regions or work environments (to avoid bias). Ensure data collectors are adequately trained and conversant with all capability and KPI data collection instruments. Ensure that the assessors Have all assessment materials and needs, including checklists, physical verification lists, guides and instructions, glossary of terms, pre-prepared transportation routings. Hold welcome and introductory/in-brief sessions with site staff and request right, knowledgeable HF staff for the interviews.

## Slide 12: Common Issues and Resolution VII
Risk | Mitigation
Not enough time at each site | Have enough data collectors – typically 2 to 3 per team (1 does capability interview and the other 2 collect KPI data). In general, plan to visit one site per day to allow travel time, waiting time, unforeseen delays. Have a manageable list of tracer commodities (8-12) – having more will slow down data collection
Not enough time to visit all sites | Budget enough time to be able to visit all sampled sites. Involve health institutions in planning, who know the geography and terrain. Ensure enough teams ahead of time.

## Slide 13: Common Issues and Resolution VIII
Risk | Mitigation
Data Collectors not fully knowledgeable of health system | Use data collectors who are familiar with the country health system (e.g. district pharmacists or other supervisory personnel).
Staff not aware of visit in advance | If advance notification is the standard procedure, request the MOH to send the notification and physical verification lists to sites well in advance of the site visit. Reconfirm the appointments 2 days to a week before the visit date to ensure site staff will be ready and available for you. See user guide for pros and cons of advance notification.
Notes: The cons of advance notification include the possibility that the facilities will “clean up” the facility because they know an assessment team is coming. They could also prepare documents they don’t normally have on hand. In these instances the field team would not be seeing the normal state of the facility.

## Slide 14: Common Issues and Resolution IX
Risk | Mitigation
Staff resistant to let data collectors document info on negative findings as this could be perceived sensitively by their supervisors or higher levels. | Report and present findings in a professional and palatable way while maintaining integrity of assessment.
Notes: The assessment team should obtain a letter from the MOH endorsing the assessment and asking the facilities to participate. Let the staff know the data will be aggregated and not presented by facility (except at the central level). Make sure the staff realize this is not an audit.